## April 22
Site | April No. Visits | Week 1 Planned | Week 1 Actual | Week 2 Planned | Week 2 Actual | Week 3 Planned | Week 3 Actual | Week 4 Planned | Week 4 Actual | Visits Completed for Month
Abbeygate Court - Jaguar House & Mercedes House | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April |  |  | 25/4/2022 | 2
Alder Close (2 & 18) | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April | 21/4/2022 |  |  | 2
Aspen Way | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April | 22/4/2022 |  |  | 2
Bailey Grove, Lesley Way & Loakes Close - Brampton | 2 | w/c 4th April |  |  |  | w/c 18th April | 21/4/2022 |  | 25/4/2022 | 2
Barnabas Court - Cambridge Way, Milton | 2 |  | 2022-04-05 | w/c 11th April |  |  |  | w/c 25th April | 26/4/2022 | 2
Beaumont Close - Hartford | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April |  |  | 25/4/2022 | 2
Blenheim Close - Shepreth No Herbicide Use | 2 |  |  | w/c 11th April | 21/4/2022 |  |  | w/c 25th April |  | 1
Borley Way and High Street - Teversham | 2 |  |  | w/c 11th April |  |  |  | w/c 25th April | 26/4/2022 | 1
Borough Close | 1 | w/c 4th April |  |  |  |  | 21/4/2022 |  |  | 1
Burling Way | 2 |  |  | w/c 11th April | 14/4/2022 |  | 22/4/2022 | w/c 25th April |  | 2
Burtons - Meldreth | 2 |  |  | w/c 11th April |  |  | 21/4/202 | w/c 25th April |  | 1
California Road | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April |  |  | 25/4/2022 | 2
Campkin Court | 1 | [6 empty] | w/c 25th April | 29/4/2022 | 1
Challis Close | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 27/4/2022 | 2
Chapel Avenue - Wisbech St Mary | 1 | w/c 4th April | 2022-04-06 | [6 empty] | 1
Chequers Close | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 26/4/2022 | 2
Chief Street and Bakers Corner | 1 | w/c 4th April |  |  | 2022-11-04 |  |  |  |  | 1
Church Lane - Guildern Morden | 2 |  | 2022-01-04 | w/c 11th April | 13/4/2022 |  |  | w/c 25th April | 28/4/2022 | 3
Cocketts Drive | 2 | w/c 4th April |  |  |  | w/c 18th April | 21/4/2022 |  |  | 1
Cooke's Field - Waterbeach | 2 |  |  | w/c 11th April | 14/4/2022 |  |  | w/c 25th April | 28/4/2022 | 2
Copperfields | 1 | w/c 4th April | 2022-04-06 | [6 empty] | 1
Cornfield Lane, Tilling Way - Littleport | 1 | w/c 4th April |  | 2022-11-04 | [5 empty] | 1
Cornmill (including 3,4,5) | 2 | w/c 4th April |  |  |  | w/c 18th April | 21/4/2022 |  | 25/4/2022 | 2
Cornwell Close | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April | 22/4/2022 |  |  | 2
Corona House - Corona Road | 1 | [6 empty] | w/c 25th April | 29/4/2022 | 1
Cyprian Rust Way - Evens | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April | 22/4/22022 |  |  | 2
Cyprian Rust Way - Odds | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April | 22/4/2022 |  |  | 2
Danesbury Court | 2 |  |  | w/c 11th April | 2022-04-11 |  |  | w/c 25th April | 26/4/2022 | 2
Daniels End | 2 | w/c 4th April | 2022-05-04 |  |  | w/c 18th April | 20/4/2022 |  |  | 2
Desmonds Close - Harston | 2 |  | 2022-05-04 | w/c 11th April |  |  | 21/4/2022 | w/c 25th April |  | 2
Douglas Court and Prickwillow Road | 2 | w/c 4th April | 2022-11-04 |  |  | w/c 18th April |  |  | 26/4/2022 | 2
Dryden Court | 1 | w/c 4th April | 2022-04-05 |  |  |  | 21/4/2022 |  |  | 2
Durrant Close | 2 |  |  | w/c 11th April | 13/4/2022 |  |  | w/c 25th April | 29/4/2022 | 2
Duxford Road - Duxford | 1 | [6 empty] | w/c 25th April | 28/4/2022 | 1
Elderberry Close and School Road - Littleport | 2 | w/c 4th April | 2022-04-11 |  |  | w/c 18th April |  |  | 26/4/2022 | 2
Ellis House - 70 Mulberry Close | 2 |  | 2022-05-04 | w/c 11th April |  |  |  | w/c 25th April | 29/4/2022 | 2
Fairhaven | 2 |  |  | w/c 11th April |  |  |  | w/c 25th April | 28/4/22022 | 1
Fawnlea and Friar Way | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April | 20/4/2022 |  |  | 2
Foxwood South | 1 | w/c 4th April | 2022-04-07 | [6 empty] | 1
Gadwall Way & Kingfisher Drive | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April | 22/4/2022 |  |  | 2
Galfrid Close No Herbicide Use | 1 | [6 empty] | w/c 25th April | 26/4/2022 | 1
Gateway Gardens | 1 | w/c 4th April |  |  | 13/4/2022 |  |  |  |  | 1
George Pateman Court Weekly Litter & Leaf Collection GRASS FORTNIGHTLY | 4 | w/c 4th April | 2022-04-04 | w/c 11th April | 11.04/2022 | w/c 18th April | 19/4/2022 | w/c 25th April | 26/4/2022 | 4
Glebe Close | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April |  |  | 25/4/2022 | 2
Handley Drive | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April | 20/4/2022 |  |  | 2
Harebell Close | 2 | w/c 4th April |  |  |  | w/c 18th April | 21/4/2022 |  | 26/4/2022 | 2
Harvest Way and The Barns - Littleport | 1 | w/c 4th April | 2022-11-04 | [6 empty] | 1
Hassock Way | 1 | w/c 4th April | 2022-04-06 | [6 empty] | 1
Hawes Lane - Wicken | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April | 22/4/2022 |  |  | 2
Hay Close - Balsham | 1 |  |  | w/c 11th April |  |  |  |  | 28/4/2022 | 1
Headford Close | 1 |  |  | 13/4/2022 |  |  |  | w/c 25th April | 26/5/2022 | 2
Headlands - Hinchingbrooke | 1 | w/c 4th April | 2022-05-04 | [5 empty] | 25/4/2022 | 2
Henry Orbell Close | 2 | w/c 4th April |  |  | 13/4/2022 | w/c 18th April |  |  | 25/4/2022 | 2
Heron Croft | 2 | w/c 4th April | 2022-04-07 |  |  | w/c 18th April | 22/4/2022 |  |  | 2
Hudson Road and Sterling Way | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April | 20/4/2022 |  |  | 2
Jasmine House - 1a Upherds Lane | 2 | w/c 4th April |  |  |  | w/c 18th April |  |  | 28/4/2022 | 1
John Beckett Court & Bedford House flats - Chapel Street | 2 | w/c 4th April | 2022-04-11 |  |  | w/c 18th April |  |  | 26/4/2022 | 2
John Breay Close & Meldreth Rd - Shepreth | 2 |  |  | w/c 11th April | 21/4/2022 |  |  | w/c 25th April | 28/4/2022 | 2
John Conder Court | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 30/4/2022 | 2
Kathleen Elliott Way | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 30/4/2022 | 2
Lady Jermy Way & Lapwings Close | 1 | [6 empty] | w/c 25th April | 29/4/2022 | 1
Lamb Drove | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April | 20/4/2022 |  |  | 2
Malden Close | 1 | [6 empty] | w/c 25th April | 26/4/2022 | 1
Maynards - Whittlesford | 1 |  |  |  | 2022-12-04 |  |  | w/c 25th April | 27/4/2022 | 2
Meadow Lane | 2 |  |  | w/c 11th April | 2022-11-04 |  |  | w/c 25th April | 26/4/2022 | 2
Mill Road Flats, Railway House & Alison House - Mill Road Weekly Litter & Leaf Collection GRASS FORTNIGHTLY | 4 | w/c 4th April | 2022-04-04 | w/c 11th April | 2022-04-11 | w/c 18th April | 19/4/2022 | w/c 25th April | 26/4/2022 | 4
Mill Yard | 1 | w/c 4th April | 2022-04-07 | [6 empty] | 1
Moorlands Close | 2 |  |  | w/c 11th April | 13/4/2022 |  |  | w/c 25th April | 28/4/2022 | 2
Muttongate, St Clements Passage | 1 | w/c 4th April | [6 empty] | 25/4/2022 | 1
Nettleditch, Littlebury | 1 | [6 empty] | w/c 25th April | 28/4/2022 | 1
Newton Road | 2 |  |  | w/c 11th April | 21/4/2022 |  |  | w/c 25th April | 28/4/2022 | 2
Normandy Close | 2 |  | 2022-01-04 | w/c 11th April |  |  |  | w/c 25th April | 29/4/2022 | 2
Norwich Street 40 & Russell Street 82 Weekly Leaf Collection | 4 | w/c 4th April | 2022-04-04 | w/c 11th April | 2022-11-04 | w/c 18th April | 19/4/2022 | w/c 25th April | 26/4/2022 | 4
Nuffield Road Estate 1&2 Weekly Litter | 4 | w/c 4th April | 2022-04-04 | w/c 11th April | 2022-11-04 | w/c 18th April | 19/4/2022 | w/c 25th April | 26/4/2022 | 4
Old Boundary Close - Whittlesford | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 28/4/2022 | 2
Orchard Close | 2 |  |  | w/c 11th April |  |  |  | w/c 25th April | 28/4/2022 | 1
Ox Meadow | 2 |  |  | w/c 11th April | 14/4/2022 |  |  | w/c 25th April | 28/4/2022 | 2
Peacock Walk | 2 | w/c 4th April | 2022-04-05 |  |  | w/c 18th April | 21/4/2022 |  |  | 2
Peter Maitland Court & Garden Walk - Victoria Road | 2 |  |  | w/c 11th April |  |  |  | w/c 25th April | 29/4/2022 | 1
Pippin Drive | 1 |  |  |  | 13/4/2022 |  |  | w/c 25th April |  | 1
Poppy Close - Littleport | 2 | w/c 4th April |  |  | 2022-11-04 | w/c 18th April |  |  | 26/4/2022 | 2
Primrose Lane - Impington | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 27/4/2022 | 2
Pyrecroft & School Lane - Lower Cambourne | 2 | w/c 4th April | 2022-04-08 |  |  | w/c 18th April |  |  | 29/4/2022 | 2
Radegund Rd 93 | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 30/4/2022 | 2
Ribston Way 14 | 2 |  | 2022-04-04 | w/c 11th April |  |  | 19/4/2022 | w/c 25th April |  | 2
River Lane Weekly Litter | 4 | w/c 4th April | 2022-04-04 | w/c 11th April | 2022-11-04 | w/c 18th April | 19/4/2022 | w/c 25th April | 26/4/2022 | 4
Roe Walk | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April | 20/4/2022 |  |  | 2
Samuel Jones Crescent | 2 | w/c 4th April | 2022-04-05 |  |  | w/c 18th April | 21/4/2022 |  |  | 2
Saxon Close | 2 | w/c 4th April | 2022-04-11 |  |  | w/c 18th April |  |  | 26/4/2022 | 2
Sayers Crescent | 1 | w/c 4th April |  |  |  |  | 21/4/2022 |  |  | 1
Seymour Street | 2 |  |  | w/c 11th April | 2022-04-11 | 2022-12-04 |  | w/c 25th April |  | 2
Shephard Close | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April |  |  | 29/4/2022 | 2
St Andrews Glebe - 527 Coldhams Lane | 2 |  |  | w/c 11th April | 2022-12-04 |  |  | w/c 25th April | 30/4/2022 | 2
St Johns Road | 1 | w/c 4th April |  |  | 13/4/2022 |  |  |  |  | 1
Stable Yard, The Paddock & Greenhaze Lane | 1 | w/c 4th April | 2022-04-06 | [6 empty] | 1
Stanley Road | 1 | [6 empty] | w/c 25th April | 29/4/2022 | 1
Stepneys | 2 |  |  | w/c 11th April | 13/4/2022 |  |  | w/c 25th April | 30/4/2022 | 2
Sunflower Nursery - 2 High St | 1 | w/c 4th April |  |  |  |  | 20/4/2022 |  | 29/4/2022 | 2
Swansley Lane | 2 | w/c 4th April | 2022-04-06 |  |  | w/c 18th April |  |  | 30/4/2022 | 2
Tates Field | 1 | w/c 4th April | 2022-04-06 | [6 empty] | 1
Tayberry Close and Cherry Drive - Littleport | 2 | w/c 4th April | 2022-04-11 |  |  | w/c 18th April |  |  | 26/4/2022 | 2
Ten Acre Place | 1 |  |  |  | 13/4/2022 |  |  | w/c 25th April |  | 1
The Hawthorns - Balsham | 2 |  |  | w/c 11th April |  |  |  | w/c 25th April | 28/4/2022 | 1
The Squires Field | 1 |  |  |  | 14/4/2022 |  |  | w/c 25th April |  | 1
The Stack Yard - Ickleton | 2 |  |  | w/c 11th April |  |  |  | w/c 25th April | 28/4/2022 | 1
Thorpe Way 120 | 2 |  |  | w/c 11th April | 13/4/2022 |  |  | w/c 25th April | 29/4/2022 | 2
Turpyn Court | 2 |  | 2022-05-04 | w/c 11th April |  |  |  | w/c 25th April | 29/4/2022 | 2
Upherds Lane 17 | 2 | w/c 4th April |  |  |  | w/c 18th April |  |  | 26/4/2022 | 1
Victoria Way 1 | 1 |  | 2022-01-04 |  | 13/4/2022 |  |  | w/c 25th April |  | 2
Victoria Way 2 & 3 | 2 |  | 2022-01-04 | w/c 11th April | 13/4/2022 |  |  | w/c 25th April | 29/4/2022 | 3
Villiers View - Littleport | 2 | w/c 4th April |  |  | 2022-11-04 | w/c 18th April | 22/4/2022 |  |  | 2
Wagstaff Close 8B | 1 | [6 empty] | w/c 25th April | 29/4/2022 | 1
Wheatsheaf Close 1 - Windmill Close | 2 | w/c 4th April |  |  | 13/4/2022 | w/c 18th April |  |  | 27/4/2022 | 2
Wheelers Close | 1 | [6 empty] | w/c 25th April | 29/4/2022 | 1
Wickford Court | 1 | w/c 4th April | 2022-06-04 | [6 empty] | 1
Windmill Close | 2 | w/c 4th April |  |  | 13/4/2022 | w/c 18th April |  |  | 27/4/2022 | 2
Woodfield Road & Brookfield Road - Highfields | 1 | [6 empty] | w/c 25th April | 28/1/2022 | 1
Wootton Field & West Rd | 2 | w/c 4th April | 2022-04-01 |  | 13/4/2022 | w/c 18th April |  |  |  | 2
| 209 | [8 empty] | 206